## Sheet1
Project Name: |  | Mirraw Jwellary App
Date |  | 2025-04-25
Tester Name |  | Jagruti
Defect Id | QA Start Date | Defect Name | Page Name | Test steps | Test data | Actual Result | Actual Result | Screenshot/ capture | Priority | Severity | QA status | Develpoer status | Defect type
1 | 2025-04-25 | Slow Image loading | Product | 1.Open App 2. Search for ring 3.Click on product | NA | it should load the products within a secoond | it is taking more than 3 sec |  | High | High | Open |  | GUI
2 | 2025-04-25 | Missing size chart | Home page | 1.Open App 2. Search for ring 3.Click on product 4.check for decsription | NA | There should be some Size and size guide | There is no description for size |  | Meduim | High | Open |  | Database
3 | 2025-04-25 | Necklace size | Home page | 1.Open App 2. Search for ring 3.Click on product 4.check for decsription | NA | There should be some Size specification and size guide | There is size but not specification about un its description for size |  | Meduim | High | Open |  | Usability
4 | 2025-04-25 | Open in Background | Any page | 1.Open App 2. on home page | NA | when you open a app and switch to another app then you open a app it is opening newly | it should not stop in background |  | Meduim | High | Open |  | functionality
5 | 2025-04-25 | High to low Filter | All jewellery page | 1.Open App 2. on home page | NA | when apply a filter high to low it shold shows the product by price high to low | It is not showing the prodcut by high to low Price but shows the randomly |  | High | Meduim | Open |  | functionality
6 | 2025-04-25 | Low to high Filter | All jewellery page | 1.Open App 2. on home page 3.open All jewellery page | NA | when apply a filter low to High it shold shows the product by price high to low | It is not showing the product by Low to high Price but shows the randomly |  | High | Meduim | Open |  | functionality
7 | 2025-04-25 | Price filter | All jewellery page | 1.Open App 2. on home page 3.open All jewellery page 4.filter 5.price | filter apply 1-500 | when apply filter it should shows the products upto 500 rs | It showing products more thatn 500 rs |  | High | Meduim | Open |  | functionality
8 | 2025-04-25 | Brand filter | All jewellery page | 1.Open App 2. on home page 3.open All 4.filter | NA | There should be Filter for brand wise filter | there is no filter for brand |  | Meduim | Meduim | Open |  | Usability
9 | 2025-04-25 | Filter by Categoty | All jewellery page | 1.Open App 2. on home page 3.open All 4.filter 5. cateogory | NA | It should shows only category that is selcted | It showing Other products also |  | Meduim | Meduim | Open |  | Usability
10 | 2025-04-25 | Categary in filter of all jewellary page | All jewellery page | 1.Open App 2. on home page 3.open All 4.filter 5. categary | NA | There should be option for search and sort by in categary list when list is bigger | There is no search for category |  | Meduim | Meduim | Open |  | Usability
12 | 2025-04-25 | View details | Cart Page | 1.Open App 2. on home page 3.select product 4.add to cart 5.view details | NA | when click on view details it should show details of payment | the function view detail is not working |  | High | Meduim | Open |  | functionality
13 | 2025-04-25 | Cart quantity | Cart Page | 1.Open App 2. on home page 3.select product 4.add to cart | NA | when add a product cart it should be able to add more quanitity for same product | you can add only 2 to 3 quantity for some product and it is not giving any update on stock |  | Law | Law | Open |  | functionality
14 | 2025-04-25 | My wallet | my wallet | 1.Open App 2. on home page 3. clik menu 4. My wallet | NA | when click on my wallet there should be option to add money in wallet | ther is no option no option to add money |  | Meduim | Meduim | Open |  | Usability
15 | 2025-04-25 | Track order | my order | 1.Open App 2. on home page 3.my account 4.my order | Placed order | there should be traking for placed order | There is no spacific tracking tracking for placed order |  | High | High | Open |  | Usability
16 | 2025-04-25 | Text message confirmation | my order | 1.Open App 2. on home page 3.my account 4.my order | Placed order | The confirmation message shoud be send to the buyer for coinfirmation and trust | there is no text message for confirmation |  | High | High | Open |  | Usability
17 | 2025-04-25 | Replace order | my order | 1.Open App 2. on home page 3.my account 4.my order | Placed order | There should be option for replace | there is no option to replace the item |  | High | High | Open |  | functionality
18 | 2025-04-25 | Rating in product | All jewellary | 1.Open App 2. on home page 3.open All jewellery page | Placed order | There should be rating for products that is for users | There is no ratings in the products |  | High | High | Open |  | Usability
19 | 2025-04-25 | Return order | All jewellary | 1.Open App 2. on home page 3.open All jewellery page | Placed order | There should be direct return option for usability purpose | There is no Direct return in appllication But you have to mail them for processs |  | High | High | Open |  | Usability
20 | 2025-04-25 | Navigation for my order, my wallet and help | Home page | 1.Open App 2. on home page | NA | There should be Easily available to check my order and sync well | it is not synced well |  | Law | Meduim | Open |  | functionality
21 | 2025-04-25 | Under 2499 products in Home page | Home page | 1.Open App 2. on home page 3.Under 2499 | NA | it should show products under price 2499 | it is showing products of more than it |  | Law | Law | Open |  | Functionality
22 | 2025-04-25 | Address pincode | Edit/Change Addrss | 1. open app 2.on profile page 3.open my addresses 4.open add new address | 304854 | its should show pincode is wrong | it is accepting wrong and invalid credentail |  | High | Meduim | Open |  | Functionality
23 | 2025-04-25 | Address city | Edit/Change Addrss | 1. open app 2.on profile page 3.open my addresses 4.open add new address | s | it should show wrong city name warning | it is accepting wrong and invalid credentail |  | High | Meduim | Open |  | Functionality
24 | 2025-04-25 | Address state | Edit/Change Addrss | 1. open app 2.on profile page 3.open my addresses 4.open add new address | g | it should show wrong state name warning | it is accepting wrong and invalid credentail |  | High | Meduim | Open |  | Functionality
25 | 2025-04-25 | Voice search | All jewellary page | 1.Open App 2. click on home page 3.open All jewellery page | Mang tika | it should shows the product directly when search by voice | it is not showing products |  | Meduim | Meduim | Open |  | Functionality
26 | 2025-04-25 | Profile photo | My account | 1. Open App 2. click on profile 3.click on my account | NA | It should give an option for change photo | it is not clickable |  | Meduim | Meduim | Open |  | Functionality
27 | 2025-04-25 | Coupon code page load | coupen code page | 1.Open App 2. on home page 3.select product 4.add to cart 5.go to cart 6.select coupon code | NA | it should load the page within 1-4 sec | it is taking more than that |  | Meduim | High | Open |  | Usability
28 | 2025-04-25 | Other clocthing product | Home page | 1.Open App 2. Search for clothes 3.Click on product | NA | It should not show any other products in Jewellary app | It is showing like clothes,shoes,bags etc.. |  | High | High | Open |  | Database
29 | 2025-04-25 | Sign out | Login | 1.Open App 2.login | NA | it should not sign out automatically | it is siging out from login automatically |  | High | High | Open |  | functionality
30 | 2025-04-25 | function Elagance uneviled | Home page | 1.Open App 2.On home page 3.elagance uneviled | NA | it should clickable and open the products relted to it | it is not clickable |  | High | High | Open |  | Functionality
31 | 2025-04-25 | function loved by all | Home page | 1.Open App 2.On home page 3.Loved by all | NA | it should clickable and open the products relted to it | it is not clickable |  | High | High | Open |  | functionality